## FARWG Work Programme
| Draft v1.2 03-12-15 |  | FARWG-15-033
No. | FARWG Area | Item | Deliverable / Outcome | Contractor | Budget | Comments / Status | Priority | Completion | EAF Approved? | PO Number | UKOPA Strategy
1 | FDMG Continuation | Collection (& audit) of fault & leak data | Audited fault & leak data | PIE |  |  | H |  | Covered by PIE Support? |  | 1. Pipeline HSE & PS Issues
2 | FDMG Continuation | Preparation of Annual Fault Report | Annual Fault Report | PIE |  |  | H |  | Covered by PIE Support? |  | 1. Pipeline HSE & PS Issues
3 | Improvements to Fault Database | Develop non-MAHP database | Fault data report for non-MAHP pipelines | PIE |  | Ongoing by RMcC | M | End 2015 | Covered by PIE Support? |  | 1. Pipeline HSE & PS Issues
4 | Improvements to Fault Database | New database baseline | Fault data and statistics from last 20? years |  |  |  | M/L |  |  |  | 1. Pipeline HSE & PS Issues
5 | Improvements to Fault Database | Review issues associated with using ILI data | Technical note detailing pros & cons, costs and recommendation on accepting ILI data |  |  |  | M
6 | Better Use of Existing Data | Data Awareness Seminar | Seminar to improve understanding of why data collected |  |  |  | M
7 | Better Use of Existing Data | Investigate effect of digs on hit rate |  |  |  |  | M
8 | Better Use of Existing Data | Investigate effect of mitigation by management action |  |  |  |  | L
9 | Better Use of Existing Data | Develop predictive corrosion model for the industry |  |  |  |  | L
10 | Risk Assessment & FF Prediction | Review of ISRU report on data distributions | Recommendations for most statistically suitable distributions to use in 3rd party failure frequency model. | Penspen | 8157.36 | Update to previous Penspen review. Draft proposal received. Price on high side but includes work for reviewing other CoolTrans documents (see below). GDG requested revised estimate. Updated proposal received and EAF approved by Board. Awaiting PO but work started. | H | End 2015 | Y |  | 2. Management of pipeline risks
11 | Risk Assessment & FF Prediction | Review of Newcastle Uni Cooltrans failure frequency reports | Recommendations for improvements to External Interference modelling approach | Penspen |  | Needed to maintain alignment with NG modelling / best practice? | H |  |  |  | 2. Management of pipeline risks
12 | Risk Assessment & FF Prediction | 5 yearly distribution update | Distributions including data upto 2015 | Penspen |  | Update to previous Penspen work. Data not available until mid 2016 at earliest. | M |  |  |  | 2. Management of pipeline risks
13 | Risk Assessment & FF Prediction | GPG on Managing SR around ethylene pipelines | Draft Good Practice Guide | PIE |  | Collation of previous work. Draft produced - may be applicable to other pipelines? | H | end 2015 |  |  | 2. Management of pipeline risks
14 | Risk Assessment & FF Prediction | GPG on Managing SR around code pipelines | Draft Good Practice Guide | tbc |  | Based on Steve Potts document and making reference to TD/2 | H
15 | Risk Assessment & FF Prediction | GPG on Managing SR around 'oily' pipelines | Draft Good Practice Guide | tbc |  | Based on previous Rod McConnell work | M
16 | Risk Assessment & FF Prediction | GPG on 3rd party damage prediction modelling | Draft Good Practice Guide | PIE |  | Depends on completion of 10 & 11? JVH to develop EAF for work by Chris Lyons. | M | Q2 2016
17 | Risk Assessment & FF Prediction | GPG on managing & mitigating the impacts of ground movement | Draft Good Practice Guide | PIE / G Leach |  |  | M
18 | Risk Assessment & FF Prediction | GPG on hazard distance for ethylene pipelines | Draft Good Practice Guide | PIE |  | Based on R McConnell previous work. | M
19 | Improvements to Fault Database | Collect & report fault data for oily pipelines | Fault data report for oily pipelines | PIE |  | Good progress being made by Rod McConnell - Rod gave a presentation to the main meeting in November 2015 | M
20 | Risk Assessment & FF Prediction | Failure Frequency for Natural Landslides | Draft Good Practice Guide | tbc |  | New item agreed at FARWG at Dec 2015 meeting based on Geoff Leach work | M
21 | Risk Assessment & FF Prediction | Discussions with HSE re methodology | Alignment between UKOPA and HSE pipeline risk assessment methodologies | NA |  | G Goodfellow to make contact with Peter Harper | H
A | Support to FARWG | Neil Jackson secretarial support |  | NJSE |  |  | H | Ongoing | Y
B | Support to FARWG | Mike Acton technical support |  | DNV GL |  |  | H | Ongoing | Y
C | Support to FARWG | Jane Haswell technical support |  | PIE |  |  | H | Ongoing | Y?
D | Support to FARWG | Rod McConnell technical support |  | PIE |  |  | H | Ongoing | Y?

## UKOPA Strategy
Area of Interest | UKOPA Objectives
1. Pipeline Health, Safety, Environmental and Process Safety Issues | (i) To share information and learning from pipeline incidents (ii) To prepare annual reports on pipeline faults, infringements and process safety (iii) To develop good practice (iv) To publish safety bulletins (v) To develop environmental risk assessment strategy
2. Management of risks associated with pipelines | To develop risk assessment and hazard assessment methodologies and influence new standards and regulations
3. Single industry body to represent the pipeline transportation industry in all pipeline matters, including legislation and regulation | (i) To represent the industry in discussions on pipeline issues (ii) To provide information and expert opinion in a consistent manner on pipeline emergency planning and response issues
4. Effective communication | (i) To provide information and guidance for members and stakeholders via the UKOPA website (ii) To provide annual updates through publication of an annual newsletter (iii) Publication of articles