## Sheet1
| Document updated 9th March 2016 |  | Completed | Sent for approval | On track | Not yet started | Issues to be overcome
FARWG 16 006
Document No | Document | Work Group | Author | Current Status | Governance | Comments | Proposed Issue date | Date Approved and Issued | Review Date
1 | Managing Pipelines with reduced cover | PIWG | N Jackson | NB to proof read in January before sending to Governance Group. Governance forms completed | Governance Documents created and to be submitted to BD to send to board for approval Feb 2016 | Complete by NJ in 2015 but awaiting final tweaks | Mid 2015 revised to Q1 2016 in readiness for Technical Seminar - sent to Board for sign off Feb 2016 | Approved Board Meeting February 2016, Issued March 2016 | Review Date 2021
2 | Inspection and Maintenance of Buried Pipelines | PIWG | N Jackson | Final draft ready for Board approval |  | Complete – need to address Tony Stonehewer issues | Mid 2015 revised to Q1 2016 in order to reslove Board issues
3 | Process Safety Good Practice Guidance | PSWG | N Jackson |  | Final draft circulated to members and comments taken account of before sending to Board for approval on 15 November 2014 | Complete | Mid 2015 | Issued and available on the website from January 2015 | Review Date 2020
4 | Managing Pipeline Dents | PIWG | J Haswell/N Jackson | Initial Draft version developed | Governance Documents created and to be submitted to BD to send to board for approval Feb 2016 | Complete | Mid 2015 revised to Q1 2016 in readiness for Technical Seminar - sent to Board for sign off Feb 2016 | Approved Board Meeting February 2016, Issued March 2016 | Review Date 2021
5 | Managing Pipeline Sleeves | PIWG | R Owen/ N Jackson / N Barker | Sent to DNV for final comments | Governance Documents created and to be submitted to BD to send to board for approval Feb 2016 | Could start to develop the structure of the document with gaps | Mid 2015 revised to Q1 2016 in readiness for Technical Seminar - sent to Board for sign off Feb 2016 | Approved Board Meeting February 2016, Issued March 2016 | Review Date 2021
6 | Specification for Concrete Slabs | FARWG | N Jackson | Final draft ready for Board approval | Agreeement to publish so long as the picture on the front cover is changed. Governance Form completed. Governance Documents created and to be submitted to BD to send to board for approval Feb 2016 | Still awaiting final document - Completed Jan 2016 | Mid 2015 revised to Q1 2016 in readiness for Technical Seminar - sent to Board for sign off Feb 2016 | Approved Board Meeting February 2016, Issued March 2016 | Review Date 2021
7 | Managing the risk of third party thefts | IWG | P Davies | Need to establish what is current industry good practice | NB sent PD questions prior to final publication Governance Documents created and to be submitted to BD to send to board for approval Feb 2016 | Suggest a survey/questionnaire could be circulated to UKOPA members as a first step. Developed by Subgroup lead by P Davis - completed | Mid 2015 revised to Q1 2016 in readiness for Technical Seminar - sent to Board for sign off Feb 2016 | Approved Board Meeting February 2016, Issued March 2016 | Review date December 2016
8 | A Framework for Pipeline Integrity | PIWG | N Jackson | Initial Draft version developed |  | Ongoing | End 2015 - date to be revised
9 | Managing Stress Corrosion Cracking | PIWG | N Jackson (based on DNV GL document) | Technical work undertaken by DNV-GL complete. | Governance Documents created and to be submitted to BD to send to board for approval Feb 2016 | Enough information is now available to develop this document. | Mid 2015 revised to Q1 2016 in readiness for Technical Seminar - sent to Board for sign off Feb 2016 | Approved Board Meeting February 2016, Issued March 2016 | Review Date 2021
| Collecting and Reporting Fault Data | FARWG | R McConnell/ N Jackson | Enough information is currently available to start this document. |  | Use the FR1 document that Rod has produced as the starting point. | End 2015 - date to be revised
| Managing Encroaching Development and Societal Risk Around Pipelines where requirements are captured by pipeline codes | FARWG | a) N Jackson/Steve Potts | Enough information is currently available to start this document. |  | Suggest a workshop could be arranged to review/confirm current good practice as a first step. | End 2015 - date to be revised
| Managing Encroaching Development and Societal Risk Around Ethylene pipelines | FARWG | b) R McConnell / N Jackson
| Managing Encroaching Development and Societal Risk Around Oil pipelines | FARWG |  |  |  | – agreed that this also needed developing based on existing work (would also include drain down issues.)
| Emergency planning distances for major accident hazard pipelines | EPWG | N Barker/ N Jackson/ EPWG | Currently being developed within the EPWG |  | Development in progress. Issues within EPWG having been circulated for comment. These are being looked into by BD and NB | End 2015 moved to June 2016
| Managing Third Party infringements | IWG | N Barker and IWG subgroup | Need to establish what is current industry good practice |  | Following a review of member documents a sub group drafted an initial version fo the document which is being revised and will go to IWG for further review | End 2015 - date to be revised
| Modelling Third Party Damage | FARWG | PIE/ C Lyons/ G Goodfellow | Chris Lyons would be able to do this based on work previously carried out by PIE. |  | Could start to develop the structure of the document with gaps | Wait for Cooltrans work
| Managing and Mitigating the Impacts of Natural Ground Movement | FARWG | J Haswell/ N Jackson/ M Acton / S Potts | Need to establish what is current industry good practice. |  | Suggest a survey/questionnaire could be circulated to UKOPA members. Swiss Gas has a lot of knowledge in this area. | End 2016
| Managing and Mitigating the Impacts of Man Made Ground Movement | FARWG | J Haswell/ N Jackson/ M Acton/ S Potts
| Hazard distances associated with Ethylene Pipelines | IWG | R McConnell/N Jackson | Would be a summary of the work previously been undertaken by Rod McConnell |  | Could start with a review of existing completed work and a mapping of how this could be fitted into a good practice document | End 2016 - date to be revised
| Managing Seismic Risks For Pipelines | FARWG | J Haswell/ G Leech/ N Jackson | Initial work being led by the PIWG. |  | Stage 1 work in this area ongoing for UKOPA (G Leach), further work will be required before it is at a stage where a document can be developed.. | End 2017
| Decommissioning and Abandoning Pipelines | PIWG | tbc | Need to establish what is current industry good practice |  | Suggest a survey/questionnaire could be circulated to UKOPA members as a first step. | End 2017
| Managing the impact of Solar Farms | IWG | N Jackson | Works started Q4 2015 and currently nearing final draft stage. Need to commission technical work |  | John Dyson has been asked to develop a proposal for the CP work. Initial draft of the document been developed and shared with IWG subgroup | Mid 2016
| Managing the impact of Wind Farms | PIWG | N Jackson | Need to commission technical work for the electrical interference impacts |  | John Dyson has been asked to develop a proposal for the CP work. Initial draft of the document been developed and shared with IWG subgroup | Mid 2016
| Emergency Plan Testing | EPWG | N Barker | Updates of previous document - no material changes |  | Document updated and final editorial tweaks required before ready to publish | 2016-03-01
| Emergency Plan Test Proforma | EPWG | N Barker | Updates of previous document - no material changes |  | Document updated and final editorial tweaks required before ready to publish | 2016-03-01
| Emergency Plan Template | EPWG | N Barker | Updates of previous document - no material changes |  | Document updated and final editorial tweaks required before ready to publish | 2016-03-01
| Managing Unpiggable Pipelines | PIWG
| Line walking | PIWG/IWG
| Assessing Residual Drain Down from Oil Pipelines | PIWG | R McConnell | Draft 1 sent for comment