## Sheet1
UKOPA Risk Assessment and Integrity Working Group
Proposed Budget Items
PIWG 15 017
PIWG Budget Summary
[6 empty] | Spend Profile | [6 empty] | Plan
Item | Total Spend, £ | Estimate Details | Board Approval | Key contact | Delivery Date | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018
[13 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Dent Management phase 2 work | 15000 | Quote | Approved | JVH | Complete | 15000 | bar: Q1
Dent Management phase 2 challenge session | none | N/A | N/A | JVH | Complete | bar: Q2
Dent Management phase 2, FEA validation work | 9528 | Quote | Approved | JVH | End Q4 14 | 9528 | bar: Q3 to Q4
Dents and fatigue study, phase 1 - questionnaire, spreadsheet and workshop | 7000 | Quote | Approved | JVH | End Q1 15 | 2500 | 5000 | bar: Q4 to Q1
Dents and fatigue study, phase 2 - further work | 25000 | Guess |  |  |  |  | 25000 | bar: Q1 to Q2
Dents and fatigue study, phase 3 - extension | 25000 | Guess | [5 empty] | 25000 | bar: Q3 to Q4
Dents and fatigue - challenge and strategy update | 1000 | Estimate | [5 empty] | 1000 | bar: Q2
Seismic study phase 1 | 6100 | Quote | Approved |  | End Q4 14 | 5500 | bar: Q3 to Q4
Seismic study phase 2 | 6000 | Estimate |  |  |  |  | 6000 | bar: Q1 to Q2
Shallow Pipe Management | none | N/A | N/A | NJ | Complete | bar: Q4
Sleeve Assessment work part 1A - use of ILI results | 6679 | Quote | Approved | RO | End Q4 14 | 6679 | bar: Q3
Sleeve Assessment work part 1B - use of ILI results | 20000 | Estimate |  | RO |  |  | 20000 | bar: Q2 to Q3
Sleeve Assessment work part 2 |  |  |  | RO | bar: Q1 to Q3
Stress Corrosion Cracking Good Practice Guide | none | N/A
Filling for microtunnels in construction
Annual Total | [5 empty] | 39207 | 56000 | 26000 | 0 | 0 | 0 | 0
Note on A23: Pailor, Graeme: RW from Wales and West was to draft a couple of paragraphs on this by way of a possible specification (from Ambergate meeting), or review international experience