## Sheet1
UKOPA Risk Assessment and Integrity Working Group
Proposed Budget Items
[7 empty] | Spend Profile | [6 empty] | Plan
Item | Total Spend, £ | Estimate Details | Board Approval | Key contact | Status | Delivery Date | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
[14 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
SUNDRIES
Neil Jackson Support |  |  |  |  | - | - |  |  | 16000 | 16000 | 16500 | 17000 | 17500
Meeting rooms contingency |  |  |  |  | - | - |  |  | 1000 | 1000 | 1000 | 1000 | 1000
THREATS
Seismic study GPG Development | 1000 | Estimate |  |  | In progress | 2016 |  |  | 1000 | bar: Q4 to Q2
Shallow Pipe Management GPG | none | N/A | N/A | NJ | Complete
Stress Corrosion Cracking GPG | none | N/A | N/A | NJ | In progress | 2016 | bar: Q4
Man-made ground movement GPG | none | N/A | N/A | NJ | In progress | 2016 | bar: Q1 to Q4
Fatigue crack detection for pipelines under cyclic load | ? |  |  |  |  | 2018
AC corrosion | [5 empty] | 2017
MITIGATIONS
Sleeve Assessment work part 1A2 - Extension of use of ILI results |  |  |  |  | In progress | 2015
Sleeve Assessment work part 1B - use of ILI results | 20000 | Estimate |  | RO |  | 2016 |  |  | 20000
Sleeve Assessment work part 2 |  |  |  | RO |  | 2017 | bar: Q1 to Q3
Above-ground inspection techniques - state of thr art | ? |  |  |  |  | 2017
Good practice for inspection of non-piggable pipes | [5 empty] | 2018
Optimisation of preventative maintenance routines | [5 empty] | 2017
UKOPA tool for surveillance vs activity | [5 empty] | 2017
Operations and maintenance good practice | none | N/A |  | NJ / GP |  | 2016
Good Practice guide to line walking | 2000 | Estimate |  | GP |  | 2016 |  |  | 2000
Advice for calculating fatigue cycles | [5 empty] | 2018
Validate fatigue SN curves for pipelines | 5000 | Guess |  | JVH |  | 2016 |  |  | 5000
DEFECT ASSESSMENT
Dents and fatigue study, phase 1 - questionnaire, spreadsheet and workshop | 7000 | Quote | Approved | JVH | In progress | 2015 | 2500 | 5000 | bar: Q1 to Q2
Dents and fatigue study, phase 2 - further work | 25000 | Guess | bar: Q1 to Q2
Dents and fatigue study, phase 3 - extension | 25000 | Guess | bar: Q3 to Q4
Dents and fatigue - challenge and strategy update | 1000 | Estimate | bar: Q2
Calculation of dent strain and assessment criteria for repair (PhD work) | 45000 | Guess |  | Julia Race |  | 2019 |  |  | 15000 | 15000 | 15000 | bar: Q2
ILI Strain / curvature report questionnaire (MSc Project?) | 5000 | Guess |  | BD / JVH |  | 2016 |  |  | 5000
PDAM for UKOPA |  |  |  | GP |  | 2017
Weld Quality study | 45000 | Quote | Approved | JVH | In progress | 2016 |  | 45000
State of the art rewview for ILI | [5 empty] | 2018
REPAIR
State-of the art review of repair techniques | [5 empty] | 2019
MISC
Predicting failure of non-piggable pipelines | [5 empty] | 2020
Filling for microtunnels in construction | [5 empty] | 2021
Determination of 'End of Life' for pipelines | [5 empty] | 2018
Common basis and methodology for revalidation | [5 empty] | 2017
Annual Total | [6 empty] | 2500 | 50000 | 65000 | 32000 | 32500 | 18000 | 18500
Note on J14: Pailor, Graeme: Sub-group meetings to develop GPG
Note on C26: Pailor, Graeme: Scope during 2016 for 2017 work approval
Note on A27: Pailor, Graeme: to include registration, written scheme develoopment, qualitative risk screening
Note on A52: Pailor, Graeme: RW from Wales and West was to draft a couple of paragraphs on this by way of a possible specification (from Ambergate meeting), or review international experience