## Sheet1
UKOPA Risk Assessment and Integrity Working Group
Proposed Budget Items
PIWG 16 012
[7 empty] | Spend Profile | [6 empty] | Plan
Item | Total Spend, £ | Estimate Details | Board Approval | Key contact | Status | Delivery Date | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
[14 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
SUNDRIES
Neil Jackson Support |  |  |  |  | - | - |  |  | 16000 | 16000 | 16500 | 17000 | 17500
Meeting rooms contingency |  |  |  |  | - | - |  |  | 1000 | 1000 | 1000 | 1000 | 1000
THREATS
Seismic study GPG Development | 1000 | Estimate |  |  | In progress | 2016 |  |  | 1000 | bar: 2015 Q4 to 2016 Q2
Shallow Pipe Management GPG | none | N/A | N/A | NJ | Complete
Stress Corrosion Cracking GPG | none | N/A | N/A | NJ | In progress | 2016 | bar: 2015 Q4
Screening for natural ground moevement GPG (BGS work) | none | N/A | N/A | NJ | In progress | 2016 | bar: 2015 Q4
Man-made ground movement GPG | ? |  |  |  |  | 2019 | bar: 2016 Q1 to 2016 Q4
Fatigue crack detection for pipelines under cyclic load | ? |  |  |  |  | 2018
AC corrosion | [5 empty] | 2017
MITIGATIONS
Sleeve Assessment work part 1A2 - Extension of use of ILI results |  |  |  |  | In progress | 2015
Sleeve Assessment work part 1B - use of ILI results | 20000 | Estimate |  | RO |  | 2016 |  |  | 20000
Sleeve Assessment work part 2 |  |  |  | RO |  | 2017 | bar: 2015 Q1 to 2016 Q3
Above-ground inspection techniques - state of thr art | ? |  |  |  |  | 2017
Good practice for inspection of non-piggable pipes | [5 empty] | 2018
Optimisation of preventative maintenance routines | [5 empty] | 2017
UKOPA tool for surveillance vs activity | [5 empty] | 2017
Operations and maintenance good practice | none | N/A |  | NJ / GP |  | 2016
Good Practice guide to line walking | 2000 | Estimate |  | GP |  | 2016 |  |  | 2000
Advice for calculating fatigue cycles | [5 empty] | 2018
Application of fatigue SN curves in pipeline assessment | 5000 | Guess |  | JVH |  | 2016 |  |  | 5000
DEFECT ASSESSMENT
Dents and fatigue study, phase 1 - questionnaire, spreadsheet and workshop | 7000 | Quote | Approved | JVH | In progress | 2015 | 2500 | 5000 | bar: 2015 Q1 to 2015 Q2
Dents and fatigue study, phase 2 - further work - liquid pipelines | 25000 | Guess | bar: 2015 Q1 to 2015 Q2
Dents and fatigue study, phase 3 - extension - gas pipelines | 25000 | Guess | bar: 2015 Q3 to 2015 Q4
Dents and fatigue - challenge and strategy update | 1000 | Estimate | bar: 2016 Q2
Calculation of dent strain and assessment criteria for repair (PhD work) | 45000 | Guess |  | Julia Race |  | 2019 |  |  | 15000 | 15000 | 15000 | bar: 2016 Q2
ILI Strain / curvature report questionnaire (MSc Project?) | 5000 | Guess |  | BD / JVH |  | 2016 |  |  | 5000
PDAM for UKOPA |  |  |  | GP |  | 2017
Weld Quality study | 45000 | Quote | Approved | JVH | In progress | 2016 |  | 45000
State of the art review for ILI | [5 empty] | 2018
REPAIR
State-of the art review of repair techniques | [5 empty] | 2019
MISC
Decommissioning of pipelines | [5 empty] | 2020
Predicting failure of non-piggable pipelines | [5 empty] | 2021
Filling for microtunnels in construction | [5 empty] | 2018
Determination of 'End of Life' for pipelines | [5 empty] | 2017
Common basis and methodology for revalidation
[7 empty] | 2500 | 50000 | 65000 | 32000 | 32500 | 18000 | 18500
Annual Total
Note on J14: Pailor, Graeme: Sub-group meetings to develop GPG
Note on C27: Pailor, Graeme: Scope during 2016 for 2017 work approval
Note on A28: Pailor, Graeme: to include registration, written scheme develoopment, qualitative risk screening
Note on A54: Pailor, Graeme: RW from Wales and West was to draft a couple of paragraphs on this by way of a possible specification (from Ambergate meeting), or review international experience