Group 1 – Wesbsite / Communications / LinkedIn etc – UKOPA New Pipeline Engineers Group

Deliverable / Action

- New updated website

- LinkedIn UKOPA Group (Closed / managed so only members staff can join)

- Strategy for University Research projects

Timescales

- 6 months time (website scope by end March, identifying and getting content by 13th May, pass to developer for building by end June

- Immediately

- Ongoing – would need Board / working group to take on

Member Input

The group around the table were prepared to assist in developing the scope and content for the website:

Morgan James, Yan Yun Chen, Ben Morgan, Andy Skinn, Tim Rudd, Steve Bateman, Craig Alderson, Richard Price and Chris Lyons

External Input

Secretariat support from Nikki Barker

Risks / Issues

Cost of the site

Designing something not used or out of date

Need to redevelop once designed / implemented

Items identified whilst brainstorming

Deliverable is a new website (should look at the EEMUA site)

Scope / site map of requirements

Search facility

Include a section about jobs in the pipeline industry / case studies

Ask students to put in ideas for projects as university (for engagement)

Engagement with engineering Institutions / STEM Ambassadors

Google search for pipeline jobs / information

Market research regarding what should be included on the website

Do not have a dedicated Young / New pipeline engineers group – get them involved in the working groups

Welcome to the industry guide / what pipeline industry is all about

Engagement with youngsters (uni / school) via a standard presentation

Pipeline jobs – people are needed

Discussion Forum either on website or via LinkedIn Group

Masters or PHOD projects as part of the UKOPA research

Involvement in Careers Fairs.