## Forecast
UKOPA/BD/20/01
UNITED KINGDOM ONSHORE PIPELINES OPERATORS ASSOCIATION
| Updated 9th December 2020 |  |  |  | Expenditure for the Period 2020
[8 empty] | XXXXXXXXXX |  |  | XXXXXXXXXX
Activity Description |  | Sponser | Service | Relevant | 2020 | Board | Amout orginally approved | 2020 Totals and Variance to Date |  |  | Revised Forecast at end 2020 (£k) | 2021 Budget (£k) | Comment
|  |  | Provider | Information | PLAN | Approval |  | (£k)
[5 empty] | (£k) | Date | (£k) | Total Planned | Actual to Date | Variance on Expenditure to date
1 | Administration |  |  |  | 67.2 | [6 empty] | 0
1.1 | Secretariat Services | Board | PIE |  | 40 | 2019-12-01 |  | 40 | 35.699 | -4.301 | 35
1.2 | Website update and support | Secretariat | Visual |  | 4.2 | 2019-12-01 |  | 4.2 | 4.082 | -0.118 | 4.2
1.3 | Member meeting costs | Board | PIE |  | 10 | 2019-12-01 |  | 10 | 6.392 | -3.608 | 6.39
1.4 | UKOPA Brochure / newsletter (now internal) | Board | PIE |  | 0 | 2019-12-01 | 3.6 | 3.6 | 1.3 | -2.3 | 0
1.5 | Technical Seminar costs | Secretariat | Various |  | 5 | 2019-12-01 |  | 5 | 0 | -5 | 0
1.7 | Expenses | Board | PIE |  | 2 | 2019-12-01 |  | 2 | 0.67 | -1.33 | 0.7
1.8 | Members Centre Update | Board | Linux | UKOPA-EA-20-1 | 6 | 2020-02-01 |  | 6 | 5.76 | -0.24 | 6
2 | Board |  |  |  | 1 | [6 empty] | 0
2.1 | check / audit of accounts | Secretariat | B H Accountancy | Approved in 2017 | 1 | 2017-02-01 |  | 1 | 0.9 | -0.1 | 1
3 | Process Safety WG |  |  |  | 33.4 | [6 empty] | 0
3.1 | Technical support to PSWG | PSWG | PIE |  | 7.8 | 2019-12-01 |  | 7.8 | 6.5 | -1.3 | 6.5
3.3 | Preparation of PSAT Report | PSWG | PIE |  | 5.2 | 2019-12-01 |  | 5.2 | 5.2 | 0 | 5.2
3.5 | updating of PSAT software | PSWG | PIE |  | 0 | 2018-02-01 | 5.2 | 5.2 | 0 | -5.2 | 0
3.6 | GPG development for Pipeline Process Safety | PSWG | tbc |  | 9 | 2018-02-01 | 6 | 15 | 17.55 | 2.55 | 17.55
3.7 | Expenses (approximate) | PSWG | PIE |  | 1 | 2019-12-01 |  | 1 | 0.07 | -0.93 | 0.93
3.8 | GPG for behavioural safety in pipeline management | PSWG | PIE |  | 10.4 | 2019-12-01 |  | 10.4 | 0 | -10.4 | 0
4 | Infringement WG |  |  |  | 29.09 | [6 empty] | 0
4.1 | Technical and Secretarit Support to IWG | IWG | PIE |  | 7.8 | 2019-12-01 |  | 7.8 | 5.363 | -2.437 | 6.5
4.2 | Preparation of Infringement Report | IWG | PIE |  | 3.25 | 2019-12-01 |  | 3.25 | 3.25 | 0 | 3.25
4.3 | Infringement Database Management | IWG | Fisher German |  | 1.04 | 2016-02-01 |  | 1.04 | 2.88 | 1.84 | 1.04
4.7 | Expenses (approxiimate) | IWG | PIE |  | 0.5 | 2019-12-01 |  | 0.5 | 0.342 | -0.158 | 0.4
4.8 | Contractor working near HP Pipeline Docs | IWG | PIE |  | 0 | 2018-02-01 | 6.5 | 6.5 | 2.33 | -4.17 | 3
4.11 | Scoping, content and formate of UKOPA working safely DVD |  | tbc |  | 3.25 | 2019-12-01 |  | 3.25 | 0.487 | -2.763 | 1.2
4.12 | Updating of UKOPA working safetly DVD |  | tbc |  | 10 | 2019-12-01 |  | 10 | 4.11 | -5.89 | 8
4.13 | Investigation of potential for inclusion of 'infringement' module as part of agricultural college courses |  | PIE / members |  | 3.25 | 2019-12-01 |  | 3.25 | 0.65 | -2.6 | 0.65
4.14 | Production of course module if 4.12 has support |  |  |  | 0 |  |  | 0 | 0 | 0
5 | Emergency Planning WG |  |  |  | 36.8 | [6 empty] | 0
5.1 | Technical Support to EPWG | EPWG | PIE |  | 14.3 | 2019-12-01 |  | 14.3 | 9.427 | -4.873 | 12
5.2 | Admin of PERO course | EPWG | PIE |  | 6.5 | 2019-12-01 |  | 6.5 | 5.3145 | -1.1855 | 6.5
5.7 | Expenses (approximate) | EPWG | PIE |  | 1 | 2019-12-01 |  | 1 | 0.697 | -0.303 | 0.7
5.8 | Guidance notes for Senior Management on PERO requirements | EPWG | PIE |  | 0 | 2018-02-01 | 3.25 | 3.25 | 1.38 | -1.87 | 2
5.9 | Development and management of Hazard Awareness Course | EPWG | PIE |  | 0 | 2018-02-01 | 6.5 | 6.5 | 2.2 | -4.3 | 2.2
5.1 | Attendance at Emerceny Planning Conference | EPWG | PIE |  | 2 | 2018-02-01 | 1 | 3 | 2.87 | -0.13 | 2.87
5.12 | GPG identifying requirements for Emergency Planning (legislation vs good practice) | EPWG | PIE |  | 6.5 |  |  | 6.5 | 0.02 | -6.48 | 1.3
5.13 | Good pracice workshop (as per 2013) |  |  |  | 6.5 |  |  | 6.5 | 0 | -6.5 | 0
6 | Fault and Risk WG |  |  |  | 63.4 | [6 empty] | 0
6.1 | Technical Secretariat Support to FARWG (PIE) | FARWG | PIE |  | 7.8 | 2019-12-01 |  | 7.8 | 6.419 | -1.381 | 6.5
6.2 | Technical Support to FARWG (PIE) | FARWG | PIE |  | 15.6 | 2019-12-01 |  | 15.6 | 12.494 | -3.106 | 13
6.3 | Technical Support to FARWG (DNV-GL) | FARWG | DNV/GL |  | 5 | 2019-12-01 |  | 5 | 2.25 | -2.75 | 2.25
6.4 | University MSc Prize | FARWG | UKOPA |  | 0.5 | 2017-02-01 |  | 0.5 | 0.5 | 0 | 0
6.08 | Collect 2019 Fault Data and Production of report |  | PIE |  | 16.25 | 2019-12-01 |  | 16.25 | 3.007 | -13.243 | 16.25
6.09 | Data cleanse, FR1 workshop, follow up and new FR1 reporting format produced |  | PIE |  | 3.25 | 2018-02-01 | 13 | 16.25 | 16.349 | 0.099 | 1
6.1 | Continued Development of liquid hydrocarbon pipeline database |  | PIE |  | 0 | 2018-02-01 | 4.2 | 4.2 | 0 | -4.2 | 0
6.14 | Review Fault data report requirements |  | PIE |  | 0 | 2018-02-01 | 3 | 3 | 0 | -3 | 0
6.16 | Expenses (approximate) |  | RM'C |  | 2 | 2019-12-01 |  | 2 | 0.719 | -1.281 | 1.3
6.17 | Support for external presentations |  | PIE |  | 6.5 | 2019-12-01 |  | 6.5 | 0 | -6.5 | 0
6.18 | GPG Environmental analysis to demonstrate ALARP |  | PIE |  | 0 | 2018-02-01 | 13 | 13 | 0 | -13 | 0
6.19 | Support to TD1 review |  | PIE |  | 3.25 | 2019-12-01 |  | 3.25 | 4.919 | 1.669 | 5
6.2 | Support to TD2 review |  | PIE |  | 3.25 | 2019-12-01 |  | 3.25 | 0.934 | -2.316 | 1.5
7 | Pipeline Integrity WG |  |  |  | 73.3 | [6 empty] | 0
7.1 | Technical Secretariat Support to PIWG (PIE) | PIWG | PIE |  | 9.75 | 2019-12-01 |  | 9.75 | 5.525 | -4.225 | 6.5
7.2 | Technical Support to PIWG (PIE) | PIWG | PIE |  | 27.3 | 2019-12-01 |  | 27.3 | 25.279 | -2.021 | 25
7.3 | Attendence at BSI WGs and Standards Groups | PIWG | A Cosham |  | 3.25 | 2019-12-01 |  | 3.25 | 1.45 | -1.8 | 1.45
7.9 | Sleeve assessment phase 1B. Survey of ILI data and analysis | PIWG | Macaw - Moved to PIE in 2019 |  | 0 | 2017-02-01 | 20 | 20 | 2.825 | -17.175 | 3
7.13 | Development of standard for epoxy shell repairs | PIWG | Rosen |  | 10 |  | 15 | 25 | 15 | -10 | 15
7.14 | Contingency for meeting rooms | PIWG | PIE |  | 1 | 2019-12-01 |  | 1 | 0 | -1 | 0
7.15 | Weld Quality Project | PIWG | Various |  | 20 | 2019-12-01 |  | 20 | 1.95 | -18.05 | 2
7.18 | GPG DC Interference and mitigation | PIWG | P Lydon |  | 0 | 2017-02-01 | 12 | 12 | 12.2 | 0.2 | 12.2
7.22 | Expenses (approximate) | PIWG |  |  | 2 | 2019-12-01 |  | 2 | 0.435 | -1.565 | 0.5
7.24 | Budget for work that might come out of AC interference stakeholder workshop (as not sure where else it might be budgetted for unless Board want a Board project?) | PIWG | PIE / ??? |  | 0 | 2018-02-01 | 13 | 13 | 0 | -13 | 0
7.25 | Comparison of the probabilty of failure due t exernal corrosion in piggable and unpiggable pipelines | PIWG | Inc in line 7.2 |  | 0 | 2019-12-01 |  | 0 | 0 | 0 | 0
7.26 | Requirements for MOP Affirmation | PIWG | Inc in line 7.2 |  | 0 | 2019-12-01 |  | 0 | 0 | 0 | 0
7.27 | GPG for decomissioning and abandonment | PIWG | Inc in line 7.2 |  | 0 | 2019-12-01 |  | 0 | 0 | 0 | 0
8 | Governance Group |  |  |  | 14.8
8.1 | Technical Secretarial support to Governance Group | GG | PIE | BD-18-002 | 3.9 | 2019-12-01 |  | 3.9 | 3.007 | -0.893 | 3.9
8.2 | Review of GPGs (1day per guide) | GG | PIE + ?? | BD-18-002 | 6.5 | 2019-12-01 |  | 6.5 | 9.595 | 3.095 | 10
8.3 | Management of GPGs | GG | PIE | BD-18-002 | 3.9 | 2019-12-01 |  | 3.9 | 3.9 | 0 | 3.9
8.4 | Expenses (approximate) | GG | PIE | BD-18-002 | 0.5 | 2019-12-01 |  | 0.5 | 0 | -0.5 | 0
0
[5 empty] | 318.99 |  | 125.25 | 444.24 | 254.2005 | -190.0395 | 265.33
| Budgetted expenditure 2020 |  |  |  | 318.99
| Money in bank at the beginning of 2020 |  |  |  | 332.42
| Membership Fees Expected |  |  |  | 248.994
| Membership Fees to date |  |  |  | 240.694
| Monies Available 23 Dec (bank statement) |  |  |  | 368.01
Key
| UKOPA Running Costs | 214.34 |  | Planned spend 2020 (inc previously approved budget) | 444.24 |  |  | Expected WG spend for 2020 | 262.163
| Spend approved in 2020 | 104.65 |  | Opening balance plus membership fees (if all paid) | 581.414 |  |  | WG budget not being used | 39.73
| Sprend approved prior to 2020 | 125.25 |  | Money in bank (May 2020) | 424.478 |  |  | WG Carry Over to 2021 | 70.547
| Total | 444.24
|  |  |  | Revised Forecast (End Dec 2020) | 265.33
|  |  |  | spend to date (31-12-20) | 254.2005
|  |  |  | Income to date | 240.694
|  |  |  | Cash in bank | 368.01

## 5-year figures
Review of last 5 years UKOPA Financial Performance
| Year | Overall Budget | Adjusted budget during year | Actual spend | Underspend from original budget | Underspend from adjuested budget | Open Bank Balance | Closing Bank Balance | Income from members | No of members
| 2020 | 441500 |  |  |  |  | 332416.78 |  | 248994 | 30
| 2019 | 447490 | 397240 | 273520 | 173970 | 119680 | 387000 | 332416.78 | 232394 | 28
| 2018 | 410000 |  | 287454 | 122546 |  | 394000 | 387000 | 224094 | 27
| 2017 | 329000 |  | 217717 | 111283 |  | 338000 | 394000 | 224094 | 27
| 2016 | 355000 |  | 237337 | 117663 |  | 247000 | 338000 | 199200 | 24
| 2015 | 274000 |  | 188118 | 85882 |  |  | 247000 | 182600 | 22
additional info | 2013 | 211000 |  | 152000 | 59000 |  |  | 290338 | 160000 | 21
| 2002 |  |  | 55951 |  |  |  | 104000 | 73500 | 13
|  | UKOPA Running Cost | Project Costs
2020
| 2019 | 180000 | 93520

## Income B'down
UKOPA Income Summary
| Company | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2020
|  | Membership Fees | Membership Fees | Membership Fees | Membership Fees | Membership Fees | Membership Fees | Membership Fees | Membership Fees | Membership Fees | paid
1 | Shell | 15000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
2 | National Grid | 7500 | 4000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
3 | Cadent | 7500 | 4000 | 4000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
4 | Sabic | 15000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
| BP (non Member now) | 15000 | 8000 | 8000 | 8300 | 8300 | 8300 | 0 | 0 | 0 | 8300
5 | INEOS | 15000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
6 | Esso | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
7 | EON (Uniper spit out - 26 below) | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
8 | BPA | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
| BG Group (Resigned end 2014) | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
9 | CLH-PS | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
10 | Total | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
11 | Penspen | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
12 | SGN | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
13 | NGN | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
14 | Wales and the West | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
15 | GNI | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
16 | Essar | 15000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
17 | Valero | 8000 | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
18 | Swissgas | 8000 | 8000 | 8000 | 8294 | 8300 | 8294 | 8294 | 8294 | 8294 | 8294
19 | Perenco |  | 8000 | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
20 | Drax (previously Scottish Power) |  |  | 8000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
| Igas (non Member now) |  |  | 8000 | 8300 | 8300 | 8300 | 0 | 0 | 0
21 | WG PSN |  |  |  |  | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
22 | Mutual Energy |  |  |  |  | 8300 | 8300 | 8300 | 8300 | 8300 | 8300
23 | Uniper (previsouly included in EON) | [5 empty] | 8300 | 8300 | 8300 | 8300 | 8300
24 | ENI | [5 empty] | 8300 | 8300 | 8300 | 8300 | 8300
25 | Petroineos | [5 empty] | 8300 | 8300 | 8300 | 8300 | 8300
26 | Centrica | [6 empty] | 8300 | 8300 | 8300
27 | RRP | [6 empty] | 8300 | 8300 | 8300 | 8300
28 | Ineso FPS (instead of BP) | [7 empty] | 8300 | 8300 | 8300
29 | Intergen | [8 empty] | 8300 | 8300
30 | EPUKI | [8 empty] | 8300 | 8300
31
| Totals | 194000 | 160000 | 180000 | 182594 | 199200 | 224094 | 224094 | 232394 | 248994 | 240694
[6 empty] | 66400 | 74698 | 74698 | 77464.6667 | 82998

## PSWG Exp
UKOPA PSWG Budget for Workplan 2020
prepared 15/12/2019
Activity Description |  | Service | Period of | Amount to | Approved |  | % complete |  |  |  | Expenditure |  |  |  |  | Comment - December 2019 | Comment - December 2019
|  | Provider | Approval or Expenditure Approval | be Approved in 2020 | previously Amount | Spent in 2019 if project ongoing | [9 empty] | PIE rate £650 per day
|  |  |  | (£k) | (£k) |  | May | Aug | Dec | Total | May | Aug | Dec | Spend to date | Remaining
3 | Process Safety WG |  |  | 28.2 | 16.4 | [8 empty] | 29.32 | 15.28
3.1 | Technical support to PSWG | PIE |  | 7.8 | [6 empty] | 2.6 | 1.95 | 1.95 | 6.5 | 1.3 | 12 days (3 days per meeting x3) plus 3 days | on track
3.3 | Preparation of PSAT Report | PIE |  |  | 5.2 | [5 empty] | 0.65 | 3.575 | 0.975 | 5.2 | 0 | 8 days is manual | on track
3.5 | updating of PSAT software | PIE |  |  | 5.2 | [8 empty] | 0 | 5.2 | This is now going to be carried out via a spreadsheet method for the near furture so reduced from £20K to 8 days for preparing macros to do this | Not going ahead
3.6 | GPG development for Pipeline Process Safety | tbc |  | 9 | 6 | [7 empty] | 17.55 | 17.55 | -2.55 | Quoations received in 2019 for production of such a document around the £12-14K mark. Budget incresed by £8K to cover this | On track
3.7 | Expenses (approximate) |  |  | 1 | [6 empty] | 0.07 |  |  | 0.07 | 0.93
3.8 | GPG for behavioural safety in pipeline management | PIE |  | 10.4 | [9 empty] | 0 | 10.4 | 16 days budgetted for production of guide | Not going ahead but funding may be reallocated. Initially though expect to carry over
[16 empty] | Not being spent | 5.2
| Future Workloads | [14 empty] | Potentail carry over | 10.4
[16 empty] | Expected spend | 29
Mgmt of Change questions for pipelines

## IWG Exp
UKOPA IWG Budget for Workplan 2020
prepared 16/12/19
Activity Description |  | Service | Period of | Amount to | Approved |  | % complete |  |  |  | Expenditure |  |  |  |  | Comment - December 2019 | Comment - June 2020
|  | Provider | Approval or Expenditure Approval | be Approved in 2020 | previously Amount | Spent in 2019 | [9 empty] | PIE rate £650 per day
|  |  |  | (£k) | (£k) |  | May | Aug | Dec | Total | May | Aug | Dec | Actual to date | Remaining
4 | Infringement WG |  |  | 29.09 | 6.5 | [8 empty] | 19.412 | 16.178
4.1 | Technical Support to IWG | PIE |  | 7.8 | [6 empty] | 2.438 | 1.625 | 1.3 | 5.363 | 2.437 | 12 days (3 days per meeting x 3) plus 3 days | On track
4.2 | Preparation of Infringement Report | PIE |  | 3.25 | [6 empty] | 2.438 | 0.812 |  | 3.25 | 0 | 5 days | On track
4.3 | Infringement Database Management | Fisher German | 2019-21 | 1.04 | [8 empty] | 2.88 | 2.88 | -1.84 | £1036.64 per year for 3 years
4.7 | Expenses (approxiimate) |  |  | 0.5 | [6 empty] | 0.1 |  | 0.242 | 0.342 | 0.158
4.8 | Contractor HSE document - working near HP Pipelines | PIE |  |  | 6.5 | [5 empty] | 1.01 | 0.995 | 0.325 | 2.33 | 4.17 | 10 days orginally budgetted, XX spent and YY carried over | Document completed and ready to go to print. There could be some carry over which will be used to update the Landowner version so the 2 align
4.11 | Scoping, content and formate of UKOPA working safely DVD | tbc |  | 3.25 | [6 empty] | 0.325 | 0.162 |  | 0.487 | 2.763 |  | Scoping going ahead but may not required the whole budget forecast 3 days £1.95K spend
4.12 | Updating of UKOPA working safetly DVD | tbc |  | 10 | [8 empty] | 4.11 | 4.11 | 5.89 | initial budget to be confirmed by quotes | Some filming might take place this year, with some carryover into 2020, forcast £5K spend and £5K carry over
4.13 | Investigation of potential for inclusion of 'infringement' module as part of agricultural college courses | PIE / members |  | 3.25 | [6 empty] | 0.65 |  |  | 0.65 | 2.6 | budget for 5 days | Expected half sepnd, 2.5 days (£1.63K)
4.14 | Production of course module if 4.13 has support from the college community |  |  | 0 | Planned for 2021 but could be condidered later in 2020 | [8 empty] | 0 | 0
[16 empty] | Not being spent | 2.93
[16 empty] | Potentail carry over | 12
[16 empty] | Expected spend | 20.66

## EPWG Exp
UKOPA EPWG Budget for Workplan 2020
Prepared 11/10/2019
Activity Description |  | Service | Period of | Amount to | Approved |  | % complete |  |  |  | Expenditure |  |  |  |  | Comment - December 2019 | Comment - June 2020
|  | Provider | Approval | be Approved in 2020 | previously Amount | spent in 2019 | [9 empty] | PIE rate £650 per day
|  |  |  | (£k) | (£k) |  | May | Aug | Dec | Total | May | Aug | Dec | Spend to date | Remaining
5 | Emergency Planning WG |  |  | 36.8 | 10.75 | [8 empty] | 21.9085 | 25.6415
5.1 | Technical Support to EPWG | PIE |  | 14.3 | [6 empty] | 5.363 | 1.788 | 2.276 | 9.427 | 4.873 | 12 days (3 per meeting) + 3 days plus 10 days for Andy Fuller) | On track
5.2 | Admin of PERO course | PIE |  | 6.5 | [6 empty] | 2.6 | 1.707 | 1.0075 | 5.3145 | 1.1855 | 1/2 day per month plus 4 days | Expected underspend of 4 days (1.95K)
5.7 | Expenses (approximate) | PIE |  | 1 | [6 empty] | 0.697 |  |  | 0.697 | 0.303
5.8 | Guidance notes for Senior Management on PERO requirements | PIE |  |  | 3.25 | [6 empty] | 1.38 |  | 1.38 | 1.87 | The scope of this project is being developed and may well change , but would like the budget to be carried over | To be carried out this year
5.9 | Development and management of Hazard Awareness Course | PIE |  |  | 6.5 | 1.2 | [5 empty] | 1 |  | 2.2 | 4.3 | 10 days which was not all used for the original course development. Rest to be used for updating and running in 2020 | Spend not expected, but requested costs to run a webinar for this year - awaiting confirmation
5.1 | Attendance at Emerceny Planning Conference | PIE |  | 2 | 1 | [5 empty] | 2.87 |  |  | 2.87 | 0.13 | 1 day plus travel and conference ticket cost, now taking place as a woring group meeting at the college | £130 underspend
5.12 | GPG identifying requirements for Emergency Planning (legislation vs good practice) | PIE |  | 6.5 | [7 empty] | 0.02 |  | 0.02 | 6.48 | 10 days | Expected underspend of 4 days (1.95K)
5.13 | Good pracice workshop (as per 2013) | PIE |  | 6.5 | [9 empty] | 0 | 6.5 | 10 days | Not going to be spent this year but will look to schedule for 2021
Could this be used as the technical seminar 2020?
[16 empty] | Not being spent | 3.9
[16 empty] | Potentail carry over | 10.8
[16 empty] | Expected spend | 32.85

## FARWG Exp
UKOPA FARWG Budget for Workplan 2020
prepared 11/10/19 reviewed with S Joyce and updated on 29/10/19 - comments added. Updated with spend to date for July 1st Sept 2020
Activity Description |  | Service | Period of | Amount to | Approved |  | % complete |  |  |  | Expenditure |  |  |  |  | Comments Dec 2019 | Comments June 2020
|  | Provider | Approval or Expenditure Approval | be Approved in 2020 | previously Amount | Spent in 2019 | [9 empty] | PIE rate £650 per day
|  |  |  | (£k) | (£k) |  | May | Aug | Dec | Total | May | Aug | Dec | Total to date | Remaining
6 | Fault and Risk WG |  |  | 63.4 | 33.2 | [9 empty] | 49.009
6.1 | Technical Secretariat Support to FARWG (PIE) | PIE |  | 7.8 | [6 empty] | 2.519 | 1.3 | 2.6 | 6.419 | 1.381 | 3 meeting (x 3 days each) plus 7 extra days. | On track
6.2 | Technical Support to FARWG (PIE) | PIE |  | 15.6 | [6 empty] | 5.771 | 4.754 | 1.969 | 12.494 | 3.106 | 3 meeting (x 3 days each) plus 15 extra days incl completion of final GPGs | On track
6.3 | Technical Support to FARWG (DNV-GL) | DNV/GL |  | 5 | [8 empty] | 2.25 | 2.25 | 2.75
6.4 | University MSc Prize | UKOPA | Annual | 0.5 | [8 empty] | 0.5 | 0.5 | 0
6.08 | Collect 2019 Fault Data and Production of report | PIE |  | 16.25 | [6 empty] | 3.007 |  |  | 3.007 | 13.243 | Includes time for PIE to visit each of the members to ensure the correct data is collected 20 days | On track
6.09 | Data cleanse, FR1 workshop, follow up and new FR1 reporting format produced | PIE |  | 3.25 | 13 | 9.56 |  |  |  |  | 4.957 | 1.26 | 0.572 | 16.349 | -0.099 | Most will be spent in 2019, (will be updated after final 2019 expenditure is prepared), remaining is to be closed out first quarter 2020 | Data cleans exercise still to be carried out
6.1 | Continued Development of liquid hydrocarbon pipeline database | PIE |  |  | 4.2 | [8 empty] | 0 | 4.2 | Following on from some statistical analysis at the end of 2019, this is to be reviewed at the January FARWG meeting and expenditure agreed or removed | There has been no desire to see this progressing by the hydrocarbon members. Decision for the project to be cancelled and money reapplied for at such time as wanted. Money to be returned
6.14 | Review Fault data report requirements | PIE |  | approved in 2018 | 3 | [8 empty] | 0 | 3 | This is to be moved to 2020 - January FARWG to include an agenda item and then agree wether the line item is to remain or not | Despite numberous requests for suggestions from members to update the report, none has been received. Could compare against EGIG and Concawe report to see if thre is anything of interested that could be added but if there is no desire fom the board either, this could be returned
6.16 | Expenses (approximate) |  |  | 2 | [6 empty] | 0.71 |  | 0.009 | 0.719 | 1.281
6.17 | Support for external presentations | PIE |  | 6.5 | [9 empty] | 0 | 6.5 | Budget for 10 days for potential for weld quality presentations in both Europe and Canada / US | Given that all conferences have been cancelled / postponed this expenditure is not expected to be used - return
6.18 | GPG Environmental analysis to demonstrate ALARP | PIE |  |  | 13 | [8 empty] | 0 | 13 | 20 days including literature search, review of members docs and production of guide - a way forward is to be agreed at the January FARWG meeting | There is a want for this document to be developed and a subgroup meeting is being held on 24th June. It is expected that this work will have to be done outside of UKOPA, via a similar process to that used to engage Risktec for the PSWG Framework development
6.19 | Support to TD1 review | PIE |  | 3.25 | [6 empty] | 0.691 | 3.74 | 0.488 | 4.919 | -1.669 | This should remain at 5 days budget with a review taking place at the Sept 2020 meeting and the budget increased or reduced if required | Expected to be carried over to next year, but would like to keep in the programme
6.2 | Support to TD2 review | PIE |  | 3.25 | [6 empty] | 0.934 |  |  | 0.934 | 2.316 | This should remain at 5 days budget with a review taking place at the Sept 2020 meeting and the budget increased or reduced if required | Expected to be carried over to next year, but would like to keep in the programme
[16 empty] | Not being spent | 13.7
[16 empty] | Potentail carry over | 13.647
[16 empty] | Expected spend | 69.253

## PIWG Exp
UKOPA PIWG Budget for Workplan 2020
Updated 11/10/2020
Activity Description |  | Service | Period of | Amount to | Approved |  | % Completion |  |  |  | Expenditure (to date) |  |  |  |  | Comment - December 2019 | Comment - December 2020 | Comment - June 2020
|  | Provider | Approval | be Approved in 2020 | previously Amount | Spend in 2019 (or previous) | [9 empty] | PIE rate £650 per day
|  |  |  | (£k) | (£k) |  | May | Aug | Dec | Total | May | Aug | Dec | Spend to date | Remaining
7 | Pipeline Integrity WG |  |  | 72.3 | 61 | [8 empty] | 64.664 | 68.636
7.1 | Technical Secretariat Support to PIWG (PIE) | PIE |  | 9.75 | [6 empty] | 2.6 | 0.65 | 2.275 | 5.525 | 4.225 | 3meetings x 3 days plus 6 days |  | On track
7.2 | Technical Support to PIWG (PIE) | PIE |  | 27.3 | [6 empty] | 19.019 |  | 6.26 | 25.279 | 2.021 | 30 days document development (7.25, .26 and .27) plus 2 people at 3 meetings total 42 days |  | On track
7.3 | Attendence at BSI WGs and Standards Groups | A Cosham | BD-17-014 | 3.25 | [8 empty] | 1.45 | 1.45 | 1.8 | To be invoiced at the end of the year |  | On track
7.9 | Sleeve assessment phase 1B. Survey of ILI data and analysis | Macaw | 2016 | approved in 2016 | 20 | 2.5 |  |  |  |  | 0.325 |  |  | 2.825 | 17.175 | This work was taken back in house - managed by Barry MacKay - when Rosen request an extremely large amount for phase 2 of the project. PIE have done some analysis and are to be asked to provide an updated budget for this phase of the work. This Line will be updated when agreed |  | Proposal from PIE to do the spreadsheet analysis is £16.9K (26 days) Expected spend £11.3K with £8.7K carried over to 2021
7.13 | Development of standard for epoxy shell repairs |  |  | 10 | 15 | 15 | [7 empty] | 15 | 10 | The intial phase of the this project has been completed and invoiced by Rosen, however, a second phase has been requested and is being discused at the January PIWG meeting | Rosen are behind with the project | On track
7.14 | Contingency for meeting rooms |  |  |  | 1 | [8 empty] | 0 | 1 | Contingency - to be used for expnses |  | Not required
7.15 | Weld Quality Project | Various |  | 20 | [6 empty] | 1.95 |  |  | 1.95 | 18.05 | Proejct completed under currently approved budget. £20K requested for future work which will be scoped during 2020 |  | Not expecting very much spend this year. Forecast £5K with £15K carried over to 2021
7.18 | GPG DC Interference and mitigation | P Lydon | budgetted in 2018 |  | 12 | 3.12 | [5 empty] | 2.58 | 6.5 | 12.2 | -0.2 | P Lydon invoiced in 2019 for part of the development work and will invoice for the rest once it has been approved. Funding is available for roll out of the document and for Pat's support moving forward | PIWG requested a technical author prepared a signpost document for the DC and AC GPGs and the first draft has been received | On track to be spent
7.22 | Expenses (approximate) |  |  | 2 | [6 empty] | 0.435 |  |  | 0.435 | 1.565 | There will be an overspend on the expenses, which can be accounted for from the meeting room contingency line 7.14 |  | On track
7.24 | Budget for work that might come out of AC interference stakeholder workshop (as not sure where else it might be budgetted for unless Board want a Board project?) | PIE / ??? |  |  | 13 | [8 empty] | 0 | 13 | 20 days budget |  | This is unlikely to be spent this year. How do the Board want to proceed with this project. Currently cancelling
7.25 | Comparison of the probabilty of failure due t exernal corrosion in piggable and unpiggable pipelines | [14 empty] | 10 days to be included in PIE tech support budget |  | Covered in 7.2
7.26 | Requirements for MOP affirmation | [14 empty] | 10 days to be included in PIE tech support budget |  | Covered in 7.2
7.27 | GPG for decomissioning and abandonment | [14 empty] | 10 days to be included in PIE tech support budget this can be moved into 2021?? |  | Covered in 7.2
[16 empty] | Not being spent | 14 | #VALUE!
[16 empty] | Potentail carry over | 23.7 | 23.7
[16 empty] | Expected spend | 95.6 | #VALUE!
Other things for consideration
Training package for handling and storage of line pipe and fittings - this is intially going to be provided via a useful document section on the members centre
GPG for calculating vibration and piling
Pipeline decomissioning and abandonment

## Gov Exp
UKOPA Governance Group Budget for Workplan 2020
Prepared 11/10/19
Activity Description |  | Sponser | Service |  | Amount to | Approved |  | % Completion |  |  |  | Expenditure |  |  |  |  | Comment | Comment
|  |  | Provider | Expenditure approval | be Approved in 2019 | previously Amount | Previously spent | [9 empty] | PIE rate £650 per day
[5 empty] | (£k) | (£k) |  | May | Aug | Dec | Total | May | Aug | Dec | spent to date | Remaining
8 | Governance Group |  |  |  | 14.8 | 0 | [8 empty] | 16.502 | 1.223
8.1 | Technical support to Governance Group | GG | PIE | UKOPA Board Meeting - December 2020 | 3.9 | [6 empty] | 0.65 | 0.244 | 2.113 | 3.007 | 0.893 | Barry Dalus support for 6 days | Combination of all 3 line items is expected to be spent
8.2 | Review of GPGs (1day per guide) | GG | PIE + ?? | UKOPA Board Meeting - December 2020 | 6.5 | [6 empty] | 4.713 | 2.034 | 2.848 | 9.595 | -3.095 | Proof reading, editing and support from others for final version of document - 10 days budgetted | Combination of all 3 line items is expected to be spent
8.3 | Management of GPGs | GG | PIE | UKOPA Board Meeting - December 2020 | 3.9 | [6 empty] | 1.625 | 0.975 | 1.3 | 3.9 | 2.925 | Nikki Barker support for up to 6 days - prep of management information, uploading to website, etc | Combination of all 3 line items is expected to be spent
8.4 | Expenses (approximate) | GG |  |  | 0.5 | [9 empty] | 0 | 0.5
[17 empty] | Not being spent | 0
[17 empty] | Potentail carry over | 0
[17 empty] | Expected spend | 14.8